## Sheet1
| 21 | [10 empty] | 22 | [11 empty] | 23 | [11 empty] | 24
| F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M | A | M | J | J | A | S | O | N | D | J | F | M
ASSW2021 Registration Deadline | bar: 21 F
ASSW2021 Science Symposium | bar: 21 M
Foxfonna spring: Fieldwork | bar: 21 A to 21 M
UNIS Arctic Microbiology Course | bar: 21 J to 21 J
Foxfonna summer: Fieldwork | bar: 21 A to 21 S
ICPM 2022 Registration Deadline | bar: 21 D
ICPM 2022 | bar: 22 J
ICPME 2023 Abstract Deadline | bar: 22 F
Archived samples: Bioinformatics | bar: 22 A to 22 J
Archived samples: Write up | bar: 22 J
Foxfonna spring: Bioinformatics | bar: 22 A
Foxfonna spring: Write up | bar: 23 J
Goldschmidt 2023 Abstract Deadline | bar: 23 F
Foxfonna summer: Bioinformatics | bar: 23 F
Goldschmidt 2023 Regisration Deadline | bar: 23 M
ICPME 2023 Registration Deadline | bar: 23 M
ICPME 2023 | bar: 23 J
Goldschmit 2023 | bar: 23 J
Foxfonna summer: Write up | bar: 23 A to 23 S
Dormancy investigation: Lab work | bar: 23 A to 23 S
Dormancy investigation: Bioinformatics | bar: 23 A to 23 S
Dormancy investigation: Write up | bar: 23 A to 23 S
Thesis write up | bar: 23 O to 24 M
Metadata: Data collection | bar: 21 F to 21 M
Metadata: Bioinformatics | bar: 21 A to 21 J
Foxfonna spring: Lab work | bar: 21 M to 21 S
Foxfonna summer: Lab work | bar: 21 S to 21 O
Metadata: Write Up | bar: 21 O
Archived samples: Sample collection and lab work | bar: 21 N