The impact of dormancy on the biogeography and community assembly mechanisms of glacial prokaryotic communities

Amy Solman

First PhD Planning Report

Lead supervisor: Dr James Bradley

Co-Supervisor: Professor Kate Heppell

Co-Supervisor: Dr Anne Jungblut

March 2021

Table of Contents

1 Introduction	3

2 Literature Review	4

3 Knowledge Gaps	5

4 Statement of Aims & Objectives	6

5 Gantt Chart	7

6 Conferences	8

7 Research Design	9

7.1 Abbreviations	9

7.2 Cryoconite metadata analysis	9

7.2.1 Questions	9

7.2.2 Overview	9

7.2.3 Datasets	10

7.2.4 Bioinformatic analysis	10

7.2.4.1 Classification of ASVs and ecological functions	10

7.2.4.2 Quantification of abundant and rare taxa	11

7.2.4.3 Differences between communities and environmental factors	11

7.2.4.4 Geographic Analysis	11

7.2.4.5 Multivariate analysis to test for effect of spatial and environmental factors	12

7.2.4.6 Community assembly processes	12

7.2.4.7 Co-occurrence network analysis	13

7.3 Archived cryoconite analysis	13

7.3.1 Questions	13

7.3.2 Overview	14

7.3.3 Frozen sample processing	14

7.3.4 BONCAT	15

7.3.5 DNA and RNA extraction	15

7.3.6 qPCR	15

7.3.7 Amplification and sequencing	15

7.3.8 Bioinformatic analysis	15

7.4 Foxfonna spring snow, snow/ice interface and ice analysis	16

7.4.1 Questions	16

7.4.2 Overview	16

7.4.3 Sample collection	17

7.4.4 Spatial and environmental characteristics	17

7.4.5 Sequencing and bioinformatics analysis	18

7.5 Foxfonna summer cryoconite analysis	18

7.5.1 Questions	18

7.5.2 Sample collection	19

7.5.3 Measuring photosynthesis and respiration	20

7.5.4 Spatial and Environmental Characteristics	20

7.5.5 Sequencing and bioinformatics analysis	20

8 Bibliography	21

# 1 Introduction

To be completed by 29th January 2021.

# 2 Background and Literature Review

To be completed by 27th January 2021.

## 2.1 Glacial ecology

## 2.2 Cryoconite holes

## 2.3 Snow and ice ecology

## 2.4 Rare and abundant taxa

## 2.5 Microbial activity and dormancy

## 2.6 Biogeography

## 2.7 Community assembly processes

# 3 Knowledge Gaps

A major knowledge gap in the study of cryoconite ecology is the lack of differentiation between abundant and rare taxa, as well as active and dormant communities. Moreover, there has only been one previous co-occurrence network analysis of cryoconite bacteria (Gokul et al., 2016) and few studies addressing activity and dormancy (Stibal et al., 2015). To this authors knowledge, for prokaryotic cryoconite communities there has been no previous investigation of:

- Differentiation between abundant and rare taxa

- Differentiation between active and dormant communities on a Svalbard glacier

- Biogeographic patterns of abundant and rare taxa

- Biogeographic patterns of active and dormant communities

- Community assembly mechanisms of abundant and rare taxa

- Community assembly mechanisms of active and dormant communities

- Co-occurrence network analysis of abundant and rare taxa

- Co-occurrence network analysis of active and dormant communities

# 4 Aims & Objectives

- To identify the active and dormant proportions of total, abundant and rare prokaryotic taxa in cryoconite, glacial snow and ice

- To identify the relationships between dormancy, abundance and prokaryotic biogeographic patterns in cryoconite, glacial snow and ice

- To identify the relationships between dormancy, abundance and prokaryotic community assembly mechanisms in cryoconite, glacial snow and ice

- To identify the interspecific interactions of active and dormant proportions of total, abundant and rare prokaryotic taxa in cryoconite holes, glacial snow and ice

- To identify the impact of prokaryotic dormancy and abundance on photosynthesis and respiration rates in cryoconite holes

# 5 Gantt Chart

Table 1. Gantt chart of research plan from February 2021 – March 2024

# 6 Conferences

| Conference | Location | Date | Cost | Abstract Deadline | Registration Deadline | Research |
| --- | --- | --- | --- | --- | --- | --- |
| Arctic Science Summit Week (ASSW) | Online | 20th-26th March 2021 | TBC | NA | 28th February | NA |
| International Conference on Polar Microbiology (ICPM) | London, UK | 21st-22nd January 2022 | ~€250 (£223) | NA | 21st December 2021 | NA |
| International Conference on Polar Microbiology and Ecology (ICPME) | Oslo, Norway | 24th-25th June 2023 | ~€350 (£312) | 13th February 2022 | 24th May 2023 | Metadata Analysis |
| Goldschmidt Conference | Prague, Czech Republic | 9th-14th July 2023 | ~£340 | February 2023 | May 2023 | Archive/Spring Samples |

Table 2. List of conferences, locations, dates, prices and suggested research to be presented

# 7 Research Design

## 7.1 Abbreviations

| Abbreviation | Meaning |
| --- | --- |
| ASV | Amplicon sequence variant |
| OTU | Operational taxonomic unit |
| ISAR | Island species-area relationship |
| DDR | Distance-decay relationship |
| FAPROTAX | Functional annotation of prokaryotic taxa database |
| QIIME2 | Quantitative insights into microbial ecology 2 |
| CCA | Canonical correlation analysis |
| dbMEM | Distance-based Moran’s eigenvector maps |
| VPA | Variation partitioning analysis |
| βNTI | Beta-nearest taxon index |
| RCbray | Bray-Curtis based Raup-Crick |
| BONCAT | Bioorthogonal noncanonical amino acid tagging |
| qPCR | Quantitative polymerase chain reaction |
| GPS | Global positioning system |
| rDNA | Ribosomal deoxyribonucleic acid |
| cDNA | Complementary deoxyribonucleic acid |
| rRNA | Ribosomal ribonucleic acid |
| Met | L-methionine |
| AHA | L-azidohomoalanine |
| HPG | L-homopropargylglycine |

Table 3. List of abbreviations and their meanings

## 7.2 Cryoconite metadata analysis

### 7.2.1 Questions

- Are there significant differences between total, abundant and rare cryoconite communities?

- Are biogeographic patterns (ISAR/DDR) different for total, abundant and rare cryoconite communities?

- Are the deterministic and stochastic drivers of community assembly different for total, abundant and rare cryoconite communities?

- Are interspecific connections different for total, abundant and rare communities?

### 7.2.2 Overview

### 7.2.3 Datasets

DNA sequencing data from pervious cryoconite studies will be downloaded from their respective repositories. Associated spatial and environmental characteristics will also be obtained where available. Community, spatial and environmental data will be compiled into a metadata table.

### 7.2.4 Bioinformatic analysis

### 7.2.4.1 Classification of ASVs and ecological functions

QIIME2 and DADA2 will be used to process sequence libraries into ASVs rather than OTUs. ASVs offer the benefits of close-reference and do novo OTU methods in that they are reusable across studies, suitable for future use and applicable to communities lacking deep coverage in reference databases (Callahan, McMurdie, & Holmes, 2017).

Alpha diversity indices (Faith’s phylogenetic diversity (PD), Shannon’s diversity index, Chao1 and Pielou’s evenness index) will be calculated for each sample so I can use multiple indices for community comparison.

The functional annotation of prokaryotic taxa database (FAPROTAX) is a database that maps prokaryotic clades to metabolic functions (Louca et al., 2017; Louca, Parfrey, & Doebeli, 2016). It will be used to predict the ecological functions of the cryoconite prokaryotic communities and offers a cheaper alternative environmental shotgun sequencing. ASVs can be substituted for OTUs in FAPROTAX analysis (Tang et al., 2020). FAPROTAX has not been previously applied to cryoconite communities but has been used for functional annotation of bacteria from polar habitats, including: glacial ice, meltwater, meltwater river, supraglacial river, freshwater pond, talik lake, anoxic groundwater and melting permafrost active layer (Bomberg, Liljedahl, Lamminmäki, & Kontula, 2019; Zhou et al., 2019). Limitations of FAPROTAX include human error, false generalisations, the non-exhaustive database, reliance on quality and resolution of taxonomic identification, exclusion of functions with poor phylogenetic conservatism and need for manual refinement or extension of functional annotations (Louca, 2019).

### 7.2.4.2 Quantification of abundant and rare taxa

I will classify ASVs into abundant and rare groups. Differentiating between abundant and rare taxa is necessary as they can exhibit different biogeographic patterns and assembly processes (Li et al., 2021; Liu, Yang, Yu, & Wilkinson, 2015). Abundant and rare taxa will be classified based on their relative abundance in local and metacommunities (Li et al., 2021). Locally abundant ASVs are those that comprise >1% of a sample, while abundant ASVs in the metacommunity are those that comprise >0.1% of average local abundance. Locally rare ASVs are those that comprise <0.01% of a sample, whilst rare ASVs in the metacommunity are those that comprise <0.001% of average local abundance.

### 7.2.4.3 Differences between communities and environmental factors

I will use the Mann-Whitney test to compare environmental characteristics, total, abundant and rare community abundances, and alpha diversity between datasets. Pearson’s correlation analysis will be performed on microbial community abundances and spatial/environmental characteristics. Coefficient of variation will be used to illustrate abundance heterogeneity across datasets.

Cluster analysis of community composition between samples will be performed with the unweighted pair-group method with arithmetic means (UPGMA) based on Bray-Curtis distance will be used to perform cluster analysis of community composition between samples. Principal coordinates analysis (PCoA) based on Bray-Curtis distance and analysis of similarity (ANOSIM) will be used to assess differences in communities among datasets.

### 7.2.4.4 Geographic Analysis

#### Island Species-Area Relationship (ISAR)

Where cryoconite hole size data is available, analysis of the effect of island size will be carried out using Faith’s PD and ASV richness for total, abundant and rare groups. A linear model will be fit to log10-transformed Faith’s PD (as well as ASV richness) as modelled by log10-transformed cryoconite area.

#### Distance-Decay Relationship (DDR)

Using QIIME2 I will use unweighted UniFrac distances to calculate pair-wise compositional dissimilarity between cryoconite samples within and across datasets. This will be carried out using the GreenGenes database. The dissimilarity matrix will be used to test for spatial autocorrelation between cryoconite samples. Using the R package “vegan”, Mantel tests will be used to test for statistical significance in the relationship between geographic and phylogenetic distance. A linear or logistic model will be fit to the unweighted UniFrac dissimilarities as modelled by log10-transformed distance between samples (Darcy, Gendron, Sommers, Porazinska, & Schmidt, 2018).

### 7.2.4.5 Multivariate analysis to test for effect of spatial and environmental factors

Canonical correlation analysis (CCA) will be used with Distance-based Moran’s eigenvector maps (dbMEM) to investigate the impact of spatial and environmental factors on community assembly. It will indicate which spatial and environmental factors shape the total, abundant and rare microbial communities. CCA will help elucidate if total, abundant or rare groups are differentially affected by the number and type of factor.

Variation partitioning analysis (VPA) will be using to assess the relative role of spatial and environmental factors in explaining community variation. This will be done in combination with a permutation for pure effects of spatial and environmental factors.

Mantel tests will be used to verify the contributions of spatial and environmental factors on total, abundant and rare communities. Partial Mantel tests will be used to verify the contributions of spatial factors while controlling for environmental factors and vice versa. Mantel and partial mantel test results can be compared with VPA results to see if they are consistent with their interpretation.

I will also plot the number of occurrences of ASVs in samples against their average relative abundance. Spearman’s rank correlations will be calculated for the plots to assess if there is a significant positive relationship between the number of cryoconite holes occupied and the average relative abundance of ASVs to indicate if rare taxa experience limited dispersal and/or adaption.

### 7.2.4.6 Community assembly processes

I will quantify the relative contribution of community assembly processes in shaping total, abundant and rare prokaryotic communities using the analytical framework set out by Stegen et al., 2013. This framework is dependent on phylogenetic turnover so relies on more closely related ASVs exhibiting more similar habitat preferences. In order to use phylogenetic turnover to infer ecological processes I need to look for evidence of phylogenetic similarity between ASVs that share similar habitat preferences. I will carry out a phylogenetic Mantel correlogram to indicate if there are significant phylogenetic signal across relatively short phylogenetic distances (Stegen et al., 2013).

Within the framework of Stegen et al., (2013), community assembly processes may be deterministic (niche-based) or stochastic (neutral) (Table 2).

| Deterministic | Stochastic |
| --- | --- |
| Heterogenous selection (selective pressure leads to high compositional turnover) βNTI >2 | Dispersal limitation (low immigration rates lead to high compositional turnover) RCbray >0.95 |
| Homogenous selection (selective pressure leads to low compositional turnover) βNTI <-2 | Homogenising dispersal (high immigration rates lead to low compositional turnover) RCbray <-0.95 |
|  | Drift (random birth/death events lead to compositional turnover) ¦RCbray¦<0.95 |

Table 4. Deterministic and stochastic processes of community assembly included in the framework of Stegen et al., 2013

Ecological processes are evaluated using weighted β-nearest taxon index (βNTI) and Bray-Curtis based Raup-Crick (RCbray) null models. Phylogenetic turnover between the communities will be analysed using R package “picante” to calculate the weighted β-mean nearest taxon distance (βMNTD). βNTI is the number of standard deviations of the βMNTD from the null distribution. If βNTI is >2 is it suggestive of heterogenous selection, if βNTI is <-2 this is evidence of homogenous selection. If |βNTI| is <2 RCbray values are used to indicate dispersal limitation (RCbray >0.95), homogenizing dispersal (RCbray <-0.95) and drift (|RCbray|<0.95) (Table 2).

### 7.2.4.7 Co-occurrence network analysis

Community co-occurrence network models will be constructed to compare community interactions for each dataset. Co-occurrence network analysis can highlight positive (cooperative) and negative (competitive) connections between ASVs. Significant correlations will be indicated by Pearson’s correlation coefficients of >0.6 or <-0.6 with significance level <0.05 (Li et al., 2021). ASVs that are present in at least 30% of samples will be retained for network construction. I will generate a network diagram using Gephi software.

For each sample in each dataset a subnetwork will be constructed. DDRs of microbial co-occurrence patterns will be analysed by calculating subnetwork topological features, including: number of nodes and edges, average node degree, modularity, clustering coefficient, short path, length graph density, betweenness centralization, degree centralization and network diameter. The relationship between distance and co-occurrence pattern dissimilarities will be plotted and Spearman’s correlation coefficient calculated. If there is a significant positive correlation between distance and co-occurrence patterns this will be evidence for significant DDRs for total and active community network structures (i.e. the community structures are spatially autocorrelated and change with increasing distance from one another).

## 7.3 Archived cryoconite analysis

### 7.3.1 Questions

- Is there a significant difference between the active and dormant communities of total, abundant and rare taxa?

- Are biogeographic patterns (ISAR/DDR) different for active and dormant communities of total, abundant and rare cryoconite taxa?

- Are the deterministic and stochastic drivers of community assembly different for active and dormant communities of total, abundant and rare cryoconite taxa?

- Are interspecific connections different for active and dormant communities of total, abundant and rare taxa?

### 7.3.2 Overview

### 7.3.3 Frozen sample processing

To extract cells for BONCAT, and DNA/RNA samples for qPCR and sequencing, the frozen archived samples will be thawed and incubated to simulate cryoconite hole conditions.

Excess ice will be removed from the sample using a chisel, ~2mm of the sample surface will be melted away with sterile water to avoid contamination, remaining sample will be thawed at 4C, homogenised with a spatula (Darcy et al., 2018). Sediment samples will then be removed for DNA/RNA extraction and BONCAT incubations.

For BONCAT, samples from the freshly melted sediment will be added to deionized water in precooled 20mL cylindrical glass scintillation vitals and shaken briefly before allowing the sediment to settle providing an aqueous environment similar to cryoconite holes (Stibal & Tranter, 2007). The vials should then be incubated for 24hrs at temperature and irradiance levels to simulate natural conditions. For example, for samples originally collected from Svalbard irradiance value should be 85 μmol photons m−2 s−1 within the typical range of Svalbard summertime (10–1500 μmol photons m−2s−1) while water temperatures are maintained between 0.2-1.9C (Singh, Singh, & Dhakephalkar, 2014; Stibal, Elster, Šabacká, & Kaštovská, 2007). After 24hr incubation at natural temperature and irradiance the samples will further incubated following the below BONCAT procedure.

### 7.3.4 BONCAT

Bioorthogonal noncanonical amino acid tagging (BONCAT) is a method for identifying metabolically active cells by tracking the incorporation of ﻿azide‐ or alkyne-bearing methionine analogues into newly synthesized proteins (Hatzenpichler et al., 2016). BONCAT is a useful tool in tracking translational activity as non-canonical amino acids have minimal metabolic impact on cells, thus there is no significant altering of cellular physiology (Steward et al., 2020).

I will incubate cells extracted from cryoconite samples with a biorthogonal synthetic amino acid such as ﻿L-methionine (Met) surrogates L-azidohomoalanine (AHA) or L-homopropargylglycine (HPG) (Hatzenpichler et al., 2016). Translationally active cells will incorporate the synthetic amino acid into newly synthesized proteins, in place of Met. Proteins containing the synthetic amino acid will be fluorescently labelled via a Cu(I)-catalyzed azide−alkyne click reaction and quantified.

### 7.3.5 DNA and RNA extraction

Extraction kits will be used to extract DNA and RNA from cryoconite samples. RNA will be purified to remove coextracted DNA. Purified RNA will be used to synthesize complementary DNA (cDNA). DNA and cDNA will then be stored at -80°C until further analysis. DNA and cDNA will hereafter be referred to as rDNA and rRNA, respectively.

### 7.3.6 qPCR

qPCR will be used to calculate bacterial and archaeal total 16S rRNA gene abundance (rDNA) and active 16S rRNA gene transcript abundance (rRNA) for each sample. Application of rRNA/rDNA ratios for inferring the activity status of prokaryotic communities has the potential to misclassify active populations as dormant (Steven, Hesse, Soghigian, Gallegos-Graves, & Dunbar, 2017). Validation of rRNA/rDNA techniques with BONCAT will improve the interpretation of metabolic activity.

### 7.3.7 Amplification and sequencing

High-throughput sequencing of rDNA and rRNA samples will be carried out to taxonomically identify both total and active bacterial and archaeal communities.

### 7.3.8 Bioinformatic analysis

Classification of ASVs and ecological function will follow the method outlined above (3.4.1 Classification of ASVs). Additionally, ASVs will be classified as dormant or active based on rRNA:rDNA ratios (Aanderud et al., 2016). Active ASVs can will be calculated as those with rRNA%/rDNA% > 1 or 1 – (rRNA/rDNA) with a range of cutoffs. Classification of ASVs as active or dormant is sensitive to cutoffs/thresholds therefore a range will be used in further analysis (Franklin, Luria, Ozaki, & Bukaveckas, 2013). Bacterial and archaeal dormancy percentage will be estimated as the number of dormant ASVs divided by the total number of ASVs in each sample x 100.

Further bioinformatic analysis including quantification of abundant and rare taxa, differences between communities and environmental factors (where data is available), geographic analysis (where data is available), community assembly analysis and co-occurrence network analysis will also be carried out using total/active communities and dormant/active communities.

## 7.4 Foxfonna spring snow, snow/ice interface and ice analysis

### 7.4.1 Questions

- What are the differences in prokaryotic activity and abundance across snow, snow/ice interface and ice habitats?

- Is there a relationship between biogeographic patterns (ISAR/DDR) and prokaryotic activity and abundance across snow, snow/ice interface and ice habitats?

- Is there a relationship between deterministic and stochastic drivers of community assembly and prokaryotic activity and abundance across snow, snow/ice interface and ice habitats?

- Is there a relationship between interspecific connections and prokaryotic activity and abundance across snow, snow/ice interface and ice habitats?

### 7.4.2 Overview

### 7.4.3 Sample collection

Snow, snow/ice interface and ice samples will be collected from Foxfonna Glacier, Nordenskiöld Land, Svalbard (Norway), May 2021. Foxfonna is a small, cold-based Arctic glacier. Samples will be frozen at -80C until further processing.

### 7.4.4 Spatial and environmental characteristics

In-situ measurements will include: GPS coordinates, temperature, dissolved oxygen and conductivity. Snow/ice samples will also be taken from each sample site for chemical analysis. Analysis will include dissolved nutrients and major ions (Table 3).

| Dissolved Nutrients | Major Ions |
| --- | --- |
| Dissolved Organic Carbon | Chloride (Cl-) |
| Dissolved Inorganic Carbon | Sulphate (SO42-) |
| Total Dissolved Nitrogen | Calcium (﻿Ca2+) |
| Nitrite (NO2-) | Sodium (Na+) |
| Nitrate (NO3-) | Potassium (K+) |
| Ammonium (NH4+) | Magnesium (Mg2+) |
| Phosphate (PO43-) | Nitrate (NO3-) |
| Silicon dioxide (SiO2) |  |

Table 5. Dissolved nutrients and major ion concentrations for laboratory analysis

### 7.4.5 Sequencing and bioinformatics analysis

I will repeat frozen sample processing, BONCAT, DNA/RNA extraction, qPCR, sequencing and bioinformatics procedure outlined above (7.3.3-7.3.8).

## 7.5 Foxfonna summer cryoconite analysis

### 7.5.1 Questions

- Is there a significant difference in the activity and abundance of cryoconite hole taxa?

- Is there a relationship between biogeographic patterns (ISAR/DDR) and prokaryotic activity and abundance in cryoconite holes?

- Is there a relationship between deterministic and stochastic drivers of community assembly and prokaryotic activity and abundance in cryoconite holes?

- Is there a relationship between interspecific connections and prokaryotic activity and abundance in cryoconite holes?

- Are rates of photosynthesis/respiration significantly affected by differences in prokaryotic activity and abundance in cryoconite holes?

### 7.5.2 Overview

### 7.5.3 Sample collection

Cryoconite hole sediment will be collected from Foxfonna Glacier in August 2021. 30 cryoconite holes will be sampled using a spatially nested sampling scheme incorporating scales of 2, 15, and 100m as developed by Darcy, Gendron, Sommers, Porazinska, & Schmidt, 2018. The sampling regime comprises 5 triangles with sides of 15m, spaced 100m apart. 2 cryoconite holes at approximately 2m apart are sampled at each vertex of the 5 triangles (Figure 1).

Figure 1: Sampling scheme taken from Darcy et al., 2018

Cryoconite granules will be collected from the bottom of each cryoconite hole using a sterile disposable plastic pipette, placed in a sterile tube and stored at -80°C until further analysis.

### 7.5.4 Measuring photosynthesis and respiration

For approximately 5 of the sampled cryoconite holes, gross photosynthesis, respiration and net community production will be measured using the ∆CO2 24-hour incubation method (Telling et al., 2010).

### 7.5.5 Spatial and Environmental Characteristics

The spatial characteristics of each cryoconite hole will be recorded including diameter measured along north-south and east-west axes, as well as depth, using a tape measure/ruler. All other spatial and environmental measurements will follow the method set out for Foxfonna spring expedition.

### 7.5.6 Sequencing and bioinformatics analysis

Cryoconite samples will follow frozen sample processing, BONCAT, DNA/RNA extraction, qPCR, sequencing and bioinformatics procedure outlined above (7.3.3-7.3.8).

# 8 Bibliography

Aanderud, Z. T., Vert, J. C., Lennon, J. T., Magnusson, T. W., Breakwell, D. P., & Harker, A. R. (2016). Bacterial dormancy is more prevalent in freshwater than hypersaline lakes. Frontiers in Microbiology, 7(JUN), 1–13. https://doi.org/10.3389/fmicb.2016.00853

Bomberg, M., Liljedahl, L. C., Lamminmäki, T., & Kontula, A. (2019). Highly diverse aquatic microbial communities separated by permafrost in Greenland show distinct features according to environmental niches. Frontiers in Microbiology, 10(JULY). https://doi.org/10.3389/fmicb.2019.01583

Callahan, B. J., McMurdie, P. J., & Holmes, S. P. (2017). Exact sequence variants should replace operational taxonomic units in marker-gene data analysis. ISME Journal, 11(12), 2639–2643. https://doi.org/10.1038/ismej.2017.119

Darcy, J. L., Gendron, E. M. S., Sommers, P., Porazinska, D. L., & Schmidt, S. K. (2018). Island biogeography of cryoconite hole bacteria in Antarctica’s Taylor Valley and around the world. Frontiers in Ecology and Evolution, 6(NOV), 1–9. https://doi.org/10.3389/fevo.2018.00180

Franklin, R. B., Luria, C., Ozaki, L. S., & Bukaveckas, P. A. (2013). Community composition and activity state of estuarine bacterioplankton assessed using differential staining and metagenomic analysis of 16S rDNA and rRNA. Aquatic Microbial Ecology, 69(3), 247–261. https://doi.org/10.3354/ame01635

Gokul, J. K., Hodson, A. J., Saetnan, E. R., Irvine-Fynn, T. D. L., Westall, P. J., Detheridge, A. P., … Edwards, A. (2016). Taxon interactions control the distributions of cryoconite bacteria colonizing a High Arctic ice cap. Molecular Ecology, 25(15), 3752–3767. https://doi.org/10.1111/mec.13715

Hatzenpichler, R., Connon, S. A., Goudeau, D., Malmstrom, R. R., Woyke, T., & Orphan, V. J. (2016). Visualizing in situ translational activity for identifying and sorting slow-growing archaeal - bacterial consortia. Proceedings of the National Academy of Sciences of the United States of America, 113(28), E4069–E4078. https://doi.org/10.1073/pnas.1603757113

Li, M., Mi, T., He, H., Chen, Y., Zhen, Y., & Yu, Z. (2021). Active bacterial and archaeal communities in coastal sediments: Biogeography pattern, assembly process and co-occurrence relationship. Science of the Total Environment, 750, 142252. https://doi.org/10.1016/j.scitotenv.2020.142252

Liu, L., Yang, J., Yu, Z., & Wilkinson, D. M. (2015). The biogeography of abundant and rare bacterioplankton in the lakes and reservoirs of China. ISME Journal, 9(9), 2068–2077. https://doi.org/10.1038/ismej.2015.29

Louca, S. (2019). Functional Annotation of Prokaryotic Taxa (FAPROTAX). Retrieved from http://www.loucalab.com/archive/FAPROTAX/lib/php/index.php?section=Home

Louca, S., Jacques, S. M. S., Pires, A. P. F., Leal, J. S., Srivastava, D. S., Parfrey, L. W., … Doebeli, M. (2017). High taxonomic variability despite stable functional structure across microbial communities. Nature Ecology & Evolution, 1(1), 1–12. https://doi.org/10.1038/s41559-016-0015

Louca, S., Parfrey, L. W., & Doebeli, M. (2016). Decoupling function and taxonomy in the global ocean microbiome. Science (New York, N.Y.), 353(6305), 1272–1277.

Singh, P., Singh, S. M., & Dhakephalkar, P. (2014). Diversity, cold active enzymes and adaptation strategies of bacteria inhabiting glacier cryoconite holes of High Arctic. Extremophiles, 18(2), 229–242. https://doi.org/10.1007/s00792-013-0609-6

Stegen, J. C., Lin, X., Fredrickson, J. K., Chen, X., Kennedy, D. W., Murray, C. J., … Konopka, A. (2013). Quantifying community assembly processes and identifying features that impose them. ISME Journal, 7(11), 2069–2079. https://doi.org/10.1038/ismej.2013.93

Steven, B., Hesse, C., Soghigian, J., Gallegos-Graves, L. V., & Dunbar, J. (2017). Simulated rRNA/DNA ratios show potential to misclassify active populations as dormant. Applied and Environmental Microbiology, 83(11), 1–11. https://doi.org/10.1128/AEM.00696-17

Steward, K. F., Eilers, B., Tripet, B., Fuchs, A., Dorle, M., Rawle, R., … Hatzenpichler, R. (2020). Metabolic Implications of Using BioOrthogonal Non-Canonical Amino Acid Tagging (BONCAT) for Tracking Protein Synthesis. Frontiers in Microbiology, 11(February), 1–12. https://doi.org/10.3389/fmicb.2020.00197

Stibal, M., Elster, J., Šabacká, M., & Kaštovská, K. (2007). Seasonal and diel changes in photosynthetic activity of the snow alga Chlamydomonas nivalis (Chlorophyceae) from Svalbard determined by pulse amplitude modulation fluorometry. FEMS Microbiology Ecology, 59(2), 265–273. https://doi.org/10.1111/j.1574-6941.2006.00264.x

Stibal, M., Schostag, M., Cameron, K. A., Hansen, L. H., Chandler, D. M., Wadham, J. L., & Jacobsen, C. S. (2015). Different bulk and active bacterial communities in cryoconite from the margin and interior of the Greenland ice sheet. Environmental Microbiology Reports, 7(2), 293–300. https://doi.org/10.1111/1758-2229.12246

Stibal, M., & Tranter, M. (2007). Laboratory investigation of inorganic carbon uptake by cryoconite debris from Werenskioldbreen, Svalbard. Journal of Geophysical Research: Biogeosciences, 112(4), 1–9. https://doi.org/10.1029/2007JG000429

Tang, X., Xie, G., Shao, K., Hu, Y., Cai, J., Bai, C., … Gao, G. (2020). Contrast diversity patterns and processes of microbial community assembly in a river-lake continuum across a catchment scale in northwestern China. Environmental Microbiomes, 15(1), 1–17. https://doi.org/10.1186/s40793-020-00360-z

Telling, J., Anesio, A. M., Hawkings, J., Tranter, M., Wadham, J. L., Hodson, A. J., … Yallop, M. L. (2010). Measuring rates of gross photosynthesis and net community production in cryoconite holes: A comparison of field methods. Annals of Glaciology, 51(56), 153–162. https://doi.org/10.3189/172756411795932056

Zhou, L., Zhou, Y., Hu, Y., Cai, J., Liu, X., Bai, C., … Jeppesen, E. (2019). Microbial production and consumption of dissolved organic matter in glacial ecosystems on the Tibetan Plateau. Water Research, 160, 18–28. https://doi.org/10.1016/j.watres.2019.05.048